## Sheet1
Server side
Use-Cases | Class | Priority | Iterations | R | A | D | I | T | TOTAL (in days) | Cost (in €)
Initial | -- | start | I-0 | -- | -- | -- | -- | -- | 7 | 500
UC1 | User | 1 | I-1 | 10 | 5 | 17 | 35 | 13 | 10 | 15760
UC2 | Disease | 2 | I-2 | 4 | 6 | 10 | 15 | 5 | 5 | 7880
UC3 | Medicine | 4 | I-3 | 5 | 5 | 10 | 18 | 10 | 6 | 9100 |  | 2 analysists
UC4 | Notification | 6 | I-4 | 3 | 6 | 5 | 14 | 4 | 4 | 6580 |  | 3 designers
UC5 | Vaccination | 5 | I-5 | 8 | 5 | 15 | 40 | 12 | 10 | 16800 |  | 10 implementers
UC6 | Appointment | 3 | I-6 | 5 | 7 | 6 | 15 | 7 | 5 | 7540 |  | 5 Testers
Transition | -- | final | I-7 | -- | -- | -- | -- | -- | 21 | 1000 | 65160
Client Side
Use-Cases | Class | Priority | Iterations | R | A | D | I | T | TOTAL (in days) | Cost (in €)
Initial | -- | start | I-0 | -- | -- | -- | -- | -- | 7 | 500
UC1 | User | 1 | I-1 | 10 | 5 | 17 | 35 | 13 | 10 | 15760
UC2 | Disease | 2 | I-2 | 4 | 6 | 10 | 15 | 5 | 5 | 7880
UC3 | Medicine | 4 | I-3 | 5 | 5 | 10 | 18 | 10 | 6 | 9100
UC4 | Notification | 6 | I-4 | 3 | 6 | 5 | 14 | 4 | 4 | 6580
UC5 | Vaccination | 5 | I-5 | 8 | 5 | 15 | 40 | 12 | 10 | 16800
UC6 | Appointment | 3 | I-6 | 5 | 7 | 6 | 15 | 7 | 5 | 7540
Transition | -- | final | I-7 | -- | -- | -- | -- | -- | 21 | 1000 | 65160
Total
Use-Cases | Class | Priority | Iterations | R | A | D | I | T | TOTAL (in days) | Cost (in €)
Initial | -- | start | I-0 | -- | -- | -- | -- | -- | 14 | 1000
UC1 | User | 1 | I-1 | 20 | 10 | 34 | 70 | 26 | 20 | 31520
UC2 | Disease | 2 | I-2 | 8 | 12 | 20 | 30 | 10 | 10 | 15760
UC3 | Medicine | 4 | I-3 | 10 | 10 | 20 | 36 | 20 | 12 | 18200
UC4 | Notification | 6 | I-4 | 6 | 12 | 10 | 28 | 8 | 8 | 13160
UC5 | Vaccination | 5 | I-5 | 16 | 10 | 30 | 80 | 24 | 20 | 33600
UC6 | Appointment | 3 | I-6 | 10 | 14 | 12 | 30 | 14 | 10 | 15080
Transition | -- | final | I-7 | -- | -- | -- | -- | -- | 42 | 2000 | 130320
Note on N6: Analyst: 90 €/hour Designer: 60 €/hour Implementer: 30 €/hour Tester: 20 €/hour